# HMS Modernization Blueprint

VB6 + SQL Server 2008 R2 -> Phased Modern Stack

Date: 2026-09-28 | Rule: business rules preserved 1:1 — naya behavior invent nahi kiya gaya.

Evidence base: decompiled HMS.exe (351 objects), live MOONData2627 catalog (277 tables), runtime error logs, 524 Crystal Reports. Full technical detail: MODERNIZATION_BLUEPRINT.md

# 1. Measured Baseline (Charts)

Figure 1 — Top 15 tables by SQL usage in decompiled code [VERIFIED-VB6]

Core revenue chain: Depart(1378), PayCharge(873), GuestFolio(869), GuestProf(840), RevMast(835). In tables ke column semantics migration me sabse pehle freeze honge.

Figure 2 — VB6 forms/modules per module (351 total) [VERIFIED-VB6]

Front Office (55) aur POS (49) sabse bade UI surfaces hain — inhi ka test coverage sabse deep hoga.

Figure 3 — Documented bugs by severity [VERIFIED-SQL/VB6]

9 bugs registered; 2 HIGH (PayCharge duplicate-PK posting crash, hardcoded 'India12' backdoor — SRN-001).

Figure 4 — MOONData2627 live object counts [VERIFIED-SQL]

277 tables lekin 0 triggers / 0 FKs / 0 functions — saara integrity VB6 app me hai. Isliye DB-only migration kaafi nahi; service layer me rules re-create honge.

Figure 5 — Relative effort estimate [INFERRED — code volume + coupling se derived]

# 2. Target Stack

| Layer | Target |
| --- | --- |
| UI | Web app (React/Vue ya Blazor) — hotel LAN + optional cloud |
| Business logic | Service layer (FastAPI/.NET) — same rules, testable |
| Data access | Repository + server-side transactions (BUG-007 class fix) |
| Database | SQL Server 2019+ — schema pehle 1:1 compatible |
| Reports | Modern engine; .ttx field maps reuse |
| Auth | Central auth — bcrypt/argon2, lockout, claims (SRN-001) |
| Side stores | Jet .mdb (DMEPABX/Fadata/Temp/SaleTransfer) -> SQL |
| Config | Analysis.ini -> config service + secrets vault |

# 3. Phased Roadmap

Phase A — Foundation (4–6 wks): SQL upgrade, schema snapshot 1:1, auth service, CI/CD + test DB.

Phase B — Core pilot (8–12 wks): FO read-only screens, Reservation/Check-In dual-run, Night Audit service on test DB.

Phase C — Transactions (12–16 wks): Posting/Payment/Check-Out, POS+KOT, Finance vouchers + Tally export.

Phase D — Cutover (8–12 wks): remaining modules, reports replacement, VB6 retire, Jet stores migrate.

Dual-run principle: purana aur naya output side-by-side verify (PayCharge rows, bill totals, NightAuditLog) — 100% match ke bina cutover nahi.

# 4. Priority Matrix

P1: Front Office, Night Audit, Reservation (revenue core — chart1 coupling)

P2: Finance/GL, POS, Main Setup/Security

P3: Inventory, Banquet, Members/SmartCard, House Keeping

P4: HR & Payroll (SaaS option), EPABX, Messaging, Mall Mgmt

# 5. Key Risks & Mitigations

Hidden logic in 351 forms -> decomp + live SQL tracing continue; per-module freeze docs.

0 FK/0 trigger -> app-side rules document karke service layer me re-create.

Night Audit regression = revenue corruption -> exact SQL port + test-DB parallel audit + log diff.

Counter desync (BUG-003/004) -> centralized numbering service.

Report parity -> 524 .rpt me se priority wale report-by-report signoff (.ttx maps ready).

# 6. Timeline & Next Steps

Realistic total: 8–12 months phased (3–5 team members); P1 modules pehle live, VB6 parallel chalta rahega.

Owner sign-off: target stack + Phase A budget

SRN-001 containment (password rotation) — immediate

GUI walkthrough complete -> module manuals final

Front Office field-level spec freeze (screens + SQL + validations)